## Sheet1
|  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
WP1 | T1.1: Building Pipeline for Cutout Creation and Running | Year 1 Q4: D1: Repository of 3-Colour Cutouts for Entire JWST and Hubble Public Archives
T1.2: Testing and Creating Diagnostics for Zoobot Model | bar: Year 1 Q1 to Year 1 Q4
| T1.3: Running Classification and Analysis of Morphology Classifications | Year 2 Q1: R1: Release of Morphology Catalogue
WP2 | T2.1: Creating Pipeline for Matching Euclid Data | bar: Year 1 Q3 to Year 1 Q4
T2.2 Creating Pipeline for Parameterising Euclid Data and Running | bar: Year 1 Q4 to Year 2 Q2
| T2.3 Analysis of Euclid Ancillary Data and Diagnostics | Year 2 Q3: R2: Release of Full Ancillary Catalogue
WP3 | T3.1: Matching Morphology and Ancillary Catalogues | bar: Year 2 Q1 to Year 2 Q3
| T3.2: Diagnostics and Initial Analysis of Advanced Catalogue | Year 2 Q4: R3: Release of Combined Catalogue and Initial Analysis
WP4 | T4.1: Selecting Interacting Galaxies and Diagnostics | Year 3 Q1: D2: A Spectroscopically Confirmed Catalogue of Interacting Galaxies
T4.2: Identifying AGN in Sample | bar: Year 2 Q4 to Year 3 Q2
| T4.3: Morphological and Parametric Analysis | Year 3 Q4: R4: Analysis of Interacting Galaxy Catalogue and Exploration of Parameter Space Linking AGN and Interaction