## Sheet1
|  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
WP1 | T1.1: Building Pipeline | bar: Year 1 Q1 to Year 1 Q4
T1.2: Building Training Set | bar: Year 1 Q1 to Year 1 Q4
| T1.3: Diagnostics of Zoobot | Year 2 Q1: Publication of Paper 1
WP2 | T2.1: Matching to existing catalogues | bar: Year 1 Q4 to Year 2 Q1
| T2.2: Building Code for Analysis | Year 2 Q3: Publication of Paper 2
WP3 | T3.1: Acquinting self with Eucid Data | bar: Year 2 Q1 to Year 2 Q4
T3.2: Building Code for Parametric Analysis | bar: Year 2 Q1 to Year 2 Q4
| T3.3: Matching to published catalogue | Year 2 Q4: Publication of Paper 3
WP4 | T4.1: Interacting Galaxy Selection | bar: Year 2 Q2 to Year 3 Q1
T4.2: Parametric Analysis | bar: Year 2 Q4 to Year 3 Q2
| T4.3: Apply PySPAM | Year 3 Q4: Publication of Paper 4